## Business Case
1.1 Business Case
Element | Description
Problem | RetailCo has experienced flat revenue growth over the past 24 months and lacks visibility into customer behavior. There is no system to identify high-value customers or detect early signs of churn.
Opportunity | A self-service Power BI dashboard powered by a clean, automated data pipeline will enable proactive retention campaigns and inventory optimization.
Benefits | Reduce customer churn by identifying at-risk segments Improve warehouse efficiency by flagging low-revenue SKUs Enable real-time performance tracking vs. prior year (YoY)
Costs | ~20 hours of effort (self-delivered). Tools: Free-tier Jira, SQL Server Express, Power BI Desktop.
ROI | High strategic value: customer retention increases LTV; inventory rationalization frees working capital.

## Project Scope
1.2 Project Scope In Scope Ingest raw “Online Retail II” dataset into SQL Server Clean handle cancellations (invoices starting with 'C'), missing CustomerIDs, duplicates Build dimensional model: Dim_Customer, Dim_Product, Dim_Date, Fact_Sales Develop DAX measures: Revenue, MoM/YoY Growth, Return Rate, RFM Score Build Power BI dashboard with: KPI summary, product Pareto chart, RFM segmentation matrix Automate refresh via Power BI (manual or scheduled) Document solution in README & Lessons Learned Out of Scope Predictive churn modeling (ML) Integration with live ERP or CRM systems Mobile-responsive design (beyond standard Power BI capabilities) Profit margin calculation (no cost data); revenue-based proxy only

## Success Criteria (Measurable)
1.3 Success Criteria (Measurable) Dashboard refreshes automatically when source data is updated RFM segments are calculated using Recency (last 365 days), Frequency (transaction count), and Monetary (total revenue) YoY growth is accurate for overlapping date windows (e.g., Dec 2010 vs. Dec 2011) All cancellations are excluded from revenue metrics but tracked in return rate README includes data dictionary, assumptions, and known limitations

## Technology Stack
1.4 Technology Stack
Layer | Tool
Data Source | UCI “Online Retail II” (Excel .xlsx)
Data Storage | Microsoft SQL Server (LocalDB or Express)
ETL/Transformation | T-SQL (Window functions, CTEs, CASE logic)
Semantic Layer | Power BI Data Model + DAX
Visualization | Power BI Desktop
Project Mgmt | Jira (Agile + Documentation)
Documentation | Notion (for portfolio) + README.md

## Project Plan (Hybrid PRINCE2 +
⏱️ Total Timeline: 4 weeks (1 for setup/governance, 3 for delivery, 1 for closure)
2. Project Plan (Hybrid PRINCE2 + Agile)
Stage | Duration | Key Activities | Outputs
Stage 1: Initiation (PRINCE2) | Week 0 | Finalize Business Case Draft PID Define 3 core user stories Set up Jira & SQL environment | PID, Jira Board, 3 Business Questions
Stage 2: Execution (Agile) | Weeks 1–3 | Sprint 1 (Data): Ingest + clean + star schema Sprint 2 (Metrics): DAX measures (Revenue, YoY, Return %) Sprint 3 (UI): RFM logic, dashboard layout, tooltips | SQL DB, Power BI .pbix, Test cases
Stage 3: Closing (PRINCE2) | Week 4 | Final README Post-project review (Lessons Learned) Portfolio packaging | README.md, Lessons Learned log, Shareable demo

## Jira Setup
Jira Setup
Epic Name | Purpose
EPIC: Initiation (PRINCE2) | Governance & planning
EPIC: Execution - Sprint 1 (Data Engineering) | SQL pipeline
EPIC: Execution - Sprint 2 (Core Metrics) | DAX development
EPIC: Execution - Sprint 3 (UI & Analytics) | Dashboard build
EPIC: Closing (PRINCE2) | Handover & lessons